## Project Details
Project Name | Demoblaze Manual Testing
Project Type | Manual Testing
Website URL | https://www.demoblaze.com/
Created By | Esk E Alam
Date of Creation | 2024-12-27

## Test Scenarios
Test Scenario ID | Module | Test Scenario Description | Priority | Number Of Test Cases
TS01 | Sign Up | Verify user can successfully sign up | High | 2
TS02 | Login | Validate login functionality | High | 2
TS03 | Cart | Ensure cart allows product addition/removal and checkout | Medium | 4
TS04 | Cart | Validate cart persistence after logout | Medium | 1
TS05 | UI/UX | Verify UI responsiveness across devices | High | 1
TS06 | Product | Verify product listing and details page | Medium | 2
TS07 | Contact | Validate contact form submission | Medium | 2
TS08 | About Us | Test video play and popup modal | Low | 1
TS09 | Homepage | Test homepage responsiveness and navigation | High | 1

## Test Cases
Req ID | Test Case ID | Test Scenario ID | Test Title | Test Steps | Test Data | Expected Result | Actual Result | Status
R01 | TC01 | TS01 | Validate mandatory fields in sign up form with valid user data | 1.Go Signup 2.Fill-up form 3.Submit | Valid user data | User should be registered successfully | User is registered successfully | Pass
R01 | TC02 | TS01 | Validate mandatory fields in sign up form with invalid user data | 1.Go Signup 2.Fill-up form 3.Submit | Invalid user data | User should not be registered successfully | User is registered successfully | Fail
R02 | TC03 | TS02 | Validate mandatory fields in Login form with valid user data | 1.Go to Login 2.Fill-up form 3. Click Submit | Valid user data | User should login successfully | User can login successfully | Pass
R02 | TC04 | TS02 | Validate mandatory fields in Login form with invalid user data | 1.Go to Login 2.Fill-up form 3.Click Submit | Invalid user data | User should not login successfully | User can not login | Pass
R03 | TC05 | TS03 | Add product to cart | 1.Select product 2.Click Add to cart | Product list | Product should be added to cart | Product is added to cart | Pass
R03 | TC06 | TS03 | Remove product from cart | 1.Go to cart 2.Click remove | Product in cart | Product should be removed | Product is removed | Pass
R03 | TC07 | TS03 | Checkout product from cart with valid user information | 1.Go to cart 2.Click place order | Valid user information | Product order should be placed | Product order is placed successfully | Pass
R03 | TC08 | TS03 | Checkout product from cart with invalid user information | 1.Go to cart 2.Click place order | invalid user information | Product order should not be placed | Product order is placed successfully | Fail
R04 | TC09 | TS04 | Verify cart persistence after logout/login | 1.Add product 2.Logout 3.Login 4.Check cart | Existing cart data | Cart should retain products | Cart shows empty | Fail
R05 | TC10 | TS05 | Verify mobile responsiveness | Access site on mobile device | Mobile device | Site should adjust layout | Site is adjusting layout | Pass
R06 | TC11 | TS06 | Verify product details page | 1.Click on a product 2.Verify details | Any product | Product details should display | Product details is displaying | Pass
R06 | TC12 | TS06 | Test category filters | 1.Select category filter 2.Verify filtered list | Phones, Laptops, Monitors | Correct products should display | Correct products are displaying | Pass
R07 | TC13 | TS07 | Validate contact form with valid data | 1. Go to Contact Us 2.Fill form with valid data 3. Click Submit | Valid name, email, message | Submission successful message | Submission successful message is showing | Pass
R07 | TC14 | TS07 | Validate contact form with invalid data | 1. Go to Contact Us 2.Fill form with invalid data 3. Click Submit | invalid name, email, message | Error message | Submission successful message is showing | Fail
R08 | TC15 | TS08 | Verify video play | 1.Go to About Us 2.click on video play icon | - | Video should play smoothly | Video is playing smoothly | Pass
R09 | TC16 | TS09 | Test homepage banner rotation | Observe homepage for 30 sec | - | Banners should rotate correctly | Banners are rotating correctly | Pass

## RTM
Req ID | Req Description | Test Case ID
R01 | User should be able to sign up | TC01, TC02
R02 | User should be able to login | TC03, TC04
R03 | User should be able to add/remoove & checkout product from cart. | TC05, TC06.TC07,TC08
R04 | User should retain products in cart after logout/login | TC09
R05 | User should see adjusted layout across devices | TC10
R06 | User should see product details and filter products through categories | TC11 , TC12
R07 | Contact form should allow message submission | TC13 , TC14
R08 | About Us video should play without issues | TC15
R09 | Homepage should display and navigate properly | TC16

## Bug Report
Bug ID | Test Case ID | Bug Title | Bug Description | Expected Result | Actual Result | Severity & Priority | Assignee
B01 | TC02 | Data validation is not working | User can sign up with invalid data | User should not be registered successfully | User is registered successfully | High/High | Dev
B02 | TC08 | Data validation is not working | User can place order with invalid data | Product order should not be placed | Product order is placed successfully | Medium/High | Dev
B03 | TC09 | Cart is showing empty after logout/login | Cart shows empty after logout/login | Cart should retain products | Cart shows empty | Medium/High | Dev
B04 | TC14 | Contact submission form error | Contact submission is successful even with invalid data | Contact submission should show an error message | Submission successful message is showing | Medium/Medium | Dev

## Test Execution Log
Test Case ID | Execution Date | Executed By | Status | Actual Result | Defects Found | Comments | Defect Type
TC01 | 2024-12-27 | QA Tester | Pass | As expected | None
TC02 | 2024-12-27 | QA Tester | Fail | Not as expected | B01 | Sign-up allows invalid emails (e.g., 'userexample.com') without error messages | Major
TC03 | 2024-12-27 | QA Tester | Pass | As expected | None
TC04 | 2024-12-27 | QA Tester | Pass | As expected | None
TC05 | 2024-12-27 | QA Tester | Pass | As expected | None
TC06 | 2024-12-27 | QA Tester | Pass | As expected | None
TC07 | 2024-12-27 | QA Tester | Pass | As expected | None
TC08 | 2024-12-27 | QA Tester | Fail | Not as expected | B02 | Checkout proceeds with missing or invalid address and card details. | Major
TC09 | 2024-12-27 | QA Tester | Fail | Not as expected | B03 | Cart is empty after logout/login | Critical
TC10 | 2024-12-27 | QA Tester | Pass | As expected | None
TC11 | 2024-12-27 | QA Tester | Pass | As expected | None
TC12 | 2024-12-27 | QA Tester | Pass | As expected | None
TC13 | 2024-12-27 | QA Tester | Pass | As expected | None
TC14 | 2024-12-27 | QA Tester | Fail | Not as expected | B04 | Contact form submits successfully with missing or invalid data | Minor
TC15 | 2024-12-27 | QA Tester | Pass | As expected | None
TC16 | 2024-12-27 | QA Tester | Pass | As expected | None

## Test Summary Report
Total Test Cases | Passed Test Cases | Failed Test Cases | Blocked Test Cases | Defects Found | Execution Date
16 | 11 | 4 | 0 | 4 | 2024-12-27